CONTRACT AGREEMENT

SUPPLY OF EQUIPMENTS, MATERIALS AND INSTALLATION

OF

POOLS SYSTEMS

FOR

LA VISTA VILLAS PROJECT

Ref. No.: LVV-CON-005/2023

This agreement is made on 15th of May 2023,

between

PHUKET BEST WAY COMPANY LIMITED, a Thai limited liability company,  having its principal office at 48/210 Moo 4, Cherngtalay, Thalang, Phuket 83110, Thailand, register no. 0835564006464, hereinafter referred to as the “Employer” or the first party,

and

Poolnologies Co.,Ltd. registration number: 0205559031362 represented by its Director, Mr.Mattias Nordin, registered address 24/16 Moo 2, Tambon Nongprure, Amphur Banglamung, Pattaya, Chonburi 20150, THAILAND. Tel: +66 81 8408307, hereinafter referred to as the “Contractor” or the second party,

Both Parties agree to make this Contract to execute the work of construction of “SUPPLY OF EQUIPMENTS and MATERIALS of POOLS SYSTEM for LA VISTA VILLAS PROJECT (LVVP) Villas #5 and #6 (according to the Master Plan)” (hereinafter referred to as works) on the following terms and conditions.

1.	Employer’s Representative

The Employer’s Representative on this project called “The Engineer” which will be La Vista Villas Project Construction Management Team (LVVP/CM) who is responsible for supervising the contractor, administering the contract, certifying the payments due to the contractor, issuing and valuing variations to the contract, awarding extensions of time, etc.

2.	Cost of the Contract

The total cost of the works (hereinafter referred to as the “total cost”) is

802,714.00 Thai-Baht (Eight Hundred Two Thousand, Seven Hundred Fourteen Thai-Baht Only) all TAX INCLUSIVE as reflected in Annex 1 (Attached Quotation)

3.	Terms of Payment

3.1	Payments at each stage will be made by the first party:

- 1st Advance Payment: on the second party submitting an invoice upon first party’s notification about the readiness for Villa #6 equipment installation of the amount of 25% or 200,678.50 Thai-Baht (Two Hundred Thousand Six Hundred Seventy-Eight Thai-Baht And Fifty Satang). The first party’s notification should be sent not later than two weeks in advance of the designated date of delivery. The respective invoice should be paid withing five working days of the invoice receipt;

- 2nd Advance Payment: on the second party submitting an invoice upon first party’s notification about the readiness for Villa #5 equipment installation of the amount of 25% or 200,678.50 Thai-Baht (Two Hundred Thousand Six Hundred Seventy-Eight Thai-Baht And Fifty Satang). The first party’s notification should be sent not later than two weeks in advance of the designated date of delivery. The respective invoice should be paid withing five working days of the invoice receipt;

- 3d Payment: on the second party submitting an invoice upon Villa #6 equipment installation of the amount of 20% or 160,542.80 Thai-Baht (One Hundred Sixty Thousand Five Hundred Forty-Two Thai-Baht And Eighty Satang). The respective invoice should be paid withing fifteen working days of the invoice receipt;

- 4th Payment: on the second party submitting an invoice upon Villa #5 equipment installation of the amount of 20% or 160,542.80 Thai-Baht (One Hundred Sixty Thousand Five Hundred Forty-Two Thai-Baht And Eighty Satang). The respective invoice should be paid withing fifteen working days of the invoice receipt;

- 5th Payment: Release of Retention Amount of 5% or 40,135.70 Thai-Baht (Fourty Thousand One Hundred Thirty Five Thai-Baht And Seventy Satang) withing six months upon issuance of the Villa #6 Taking Over Certificate by the Employer in the absence of warranty claims;

- 6th Payment: Release of Retention Amount of 5% or 40,135.70 Thai-Baht (Fourty Thousand One Hundred Thirty Five Thai-Baht And Seventy Satang) withing six months upon issuance of the Villa #5 Taking Over Certificate by the Employer in the absence of warranty claims.

4.	Notices issuance

4.1 The first party issues a notice to the second party to visit the site for premises, piping and wiring third party works inspection not later than two weeks before the date of inspection. Second party’s relevant works acceptance is a necessary condition to proceed with equipment installation (see paragraph 4.2);

4.2 The second party notifies the first party about the readiness for the equipment installation not later than two weeks before the designated time of delivery, providing that the relevant third party works were earlier accepted by the second party;

4.3 The second party, on the works completion for each Villa, issue a notice to the first party or The Engineer nominated by the first party, to visit the site for certification of works completion. Within 7 days of the receipt of such notice, the first party or the engineer nominated by it, will ensure issue of stage completion certificate after due verification.

5.	Completion time

The works for each Villa should be completed withing one month from the date of the relevant (1st or 2nd) Advance payment. In exceptional circumstances, the time period stated in this clause may be extended in writing by mutual consent of both the parties.

6.	Extension of Time

If any of the compensation events mentioned below would prevent the work being completed by the intended completion date, the first party will decide on the intended completion date being extended by a suitable period:

- The first party does not provide the second party an access to the site or a part thereof by the agreed period.

- The first party orders a delay or does not issue completed drawings, specifications or instructions for execution of the work on time.

- Payments due to the second party are delayed without reason.

- Certification for stage completion of the work is delayed unreasonably.

7.	Liquidated and Ascertained Damages (LAD)

Any willful delay on the part of the second party in completing the construction within the stipulated period will render him liable to penalty at 0.1 % of the contract value per each day of delay subject to a limit of 10%.

8.	Duties and responsibilities of the first party

8.1	The first party shall be responsible for providing regular and frequent supervision and guidance to the second party for carrying out the works as per specifications. This will include written guidelines and regular site visit of the authorized personnel of the first party, for checking quality of material and construction to ensure that it is as per the norms.

8.2	The first party shall supply the full set of drawings and specifications to the second party for the proposed works in electronic files (pdf. and dwg.) withing 5 days after signing the current Contract. The list of supplied equipment and volume of works are stipulated by Bill Of Quantities (Annex 2) and Battery limits (Annex 3);

8.3	The first party shall timely do the payments stipulated in the Contract. Any unreasonable delay renders him liable to penalty at 0.1 % of the contract value per each day of delay subject to a limit of 10%.

9.	Duties and responsibilities of the second party

9.1	The second party shall:

- take up the works and arrange for its completion within the time period stipulated in the current Contract;

- employ suitable skilled persons to carry out the works;

- regularly supervise and monitor the progress of work;

- abide by the technical suggestions / direction of supervisory personnel;

- be responsible for bringing any discrepancy to the notice of the representative of the first party and seek necessary clarification:

- ensure that the work is carried out in accordance with specifications, drawings and within the total of the contract amount without any cost escalation;

- keep the first party informed about the progress of work;

- be responsible for all security and watch and ward arrangements at site;

- maintain necessary insurance against loss of materials/cash, etc. or workman disability compensation claims of the personnel deployed on the works as well as third party claims;

- Pay all duties, taxes and other levies payable by construction agencies as per law under the contract (First party will effect deduction from running bills in respect of such taxes as may be imposed under the law).

10.	Variations / Extra Items

The works shall be carried out by the second party in accordance with the approved drawings and specifications in the amounts, stipulated in the Annexes 2 and 3. however, if, on account of site conditions or any other factors, variations are considered necessary, the following procedure shall be followed:

- The second party shall provide the Engineer with a quotation for carrying out the Variation when requested to do so by the Engineer. The Engineer shall assess the quotation, which shall be given within seven days of the request before the Variation is ordered.

- If the quotation given by the second party is unreasonable, the Engineer may order the Variation and make a change to the Contract Price which shall be based on Engineer’s own forecast of the effects of the Variation on the Contractor’s costs.

- The second party shall not be entitled to additional payment for costs which could have been avoided by giving early warning.

11.	Securities and Defects Liability Period

Second party provides 2 years warranty period for all the works performed and equipment installed on the condition of due equipment maintenance according to the relevant user manuals.

12.	Termination

12.1	The Employer may terminate the Contract if the other party causes a fundamental breach of the Contract.

12.2	Fundamental breaches of Contract include, but shall not be limited to the following:

(a)	the contractor delays works for more than 30 days and the stoppage has not been authorized by the Engineer.

(b)	the Contractor has become bankrupt or goes into liquidation other than for a reconstruction or amalgamation.

(c)	the Engineer gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Engineer;

(d)	the Contractor does not maintain a security which is required.

12.3	Notwithstanding the above, the Employer may terminate the Contract for convenience.

12.4	If the Contract is terminated the Contractor shall stop work immediately, make the Site safe and secure and leave the Site as soon as reasonably possible.

13.	Payment upon Termination

13.1	If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Engineer shall issue a certificate for the value of the work done less advance payments received up to the date of the issue of the certificate, less other recoveries due in terms of the contract, less taxes due to be deducted at source as per applicable law.

13.2	If the Contract is terminated at the Employer’s convenience, the Engineer shall issue a certificate for the value of the work done, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works and less advance payments received up to the date of the certificate, less other recoveries due in terms of the contract and less taxes due to be deducted at source as per applicable law.

14.	Dispute settlement

If over the works, any dispute arises between the two parties, relating to any aspects of this Contract, the parties shall first attempt to settle the dispute through mutual and amicable consultation.

In the event of agreement not being reached, the matter will be referred for arbitration by a Thai Arbitrator not below the level of retired Superintending Engineer, to be appointed by the first party. The Arbitration will be conducted in accordance with the Thai Arbitration and Conciliation Act.  The decision of the Arbitrator shall be final and binding on both the parties.

15.	Contract documents

The following Documents listed hereunder shall form the part of the Contract;

Annex #1 - Quotation;

Annex #2 - Bill of Quantity;

Annex #3 – Battery limits.

The Employer and the Contractor hereby agree to the full performance of the covenants herein.

IN WITNESS WHEREOF, the parties hereto have executed this Agreement in triplicate on the day and year first above written.

Employer / First Party: ___________Mr. Vadym Bukhkalov____________

________________________________________________________

Signature& Company Stamp

__________________ Phuket Best Way Co., Ltd. _______________

________________________________________________________

Date

Contractor / Second Party: ____________Mr. Mattias Nordin____________

_________________________________________________________

Signature& Company Stamp

___________________Poolnologies Co., Ltd.____________________

_________________________________________________________

Date

Witness: ______________________		Witness: ______________________

_____________________                              _____________________

Signature					  Signature

_____________________			   _____________________

Date				                  Date